## burndown Chart
The sprint will be 2 weeks
Day | Planned | Acttual
1 | 10 | 10
2 | 10 | 7
3 | 9 | 9
4 | 7 | 8
5 | 6 | 6
6 | 5 | 6
7 | 4 | 4
8 | 3 | 2
9 | 2 | 4
10 | 1 | 1

## task board
To do | In progress | done
Checkout | Food Menu | Data Base
Cash paying | Add to basket | sign up
visa paying | Food History | log in
delivery Tracking |  | Restaurant Menu