## Product Backlog Template
# | Epic | User Story |  |  | Priority | Ready to be planned | Planned Sprint | Status
|  | As a | I want to | So that
| Create Account | user | create account | I can save my older order | 1 | developer | 5 days | done
| Access my location | user | be able to but location | delavary man can reach me easly | 1 | developer | 2 days | ready
| View Offers | user | discaound page | to show me the offer of all resturant | 3 | developer | 1 days | in progress
| Search Restaurants | user | near by me page | show me the resturant near for me | 3 | developer | 4 days | done
| Payment method | user | make account with all nessary info | I can use the future of mobile wallet | 2 | tester | 1 days | testing
| Contact method | user | enter the mobile num | I can transfer my payment to ther mobile wallet | 2 | developer | 6 days | in progress
| Reset Password | user | to have the ability to change my password | I can cahnge my passwred if I forget it | 5 | developer | 5 days | done
| Search Restaurants | user | search Restaurant | I can find new restaurant | 5 | developer | 1 days | ready
| Reviews | user | Review the restaurant | I can reach next time to the better one | 8 | developer | 1 days | testing
| View Menu | user | view menu | I can choose my food | 8 | developer | 1 days | done
| view order | Restaurant | view the users orders | I can prepare them | 13 | developer | 2 days | ready
| view location | Restaurant | view the users location | I can deliver their order | 13 | developer | 2 days | in progress
| meals changes | Restaurant | make changes to meals and offers | so that I can attract more people | 13 | developer | 2 days | testing
Sponsor Inputs
|  |  | # | High level ideas / Features
|  |  | 1 | Create Account
|  |  | 2 | View Restaurants
|  |  | 3 | Search Restaurants
|  |  | 4 | View Menu
|  |  | 5 | Add to Cart
|  |  | 6 | Purchase
|  |  | 7 | Restaurant views order
|  |  | 8 | Restaurant marks order as delivered
Notes:
|  |  | 1 | The above points were listed as draft ideas by the project sponsor.
|  |  | 2 | The project sponsor mentioned that he wants to compete against Talabat.
|  |  | 3 | As a sponsor, I am planning to compete against Talabat.
|  |  | 4 | This is a view only file, you can make a copy then edit in the copy.
|  |  | 5 | You can find a tab named Product Backlog Template, please feel free to use it when creating your product backlog.

## Sponsor Inputs
# | High level ideas / Features
1 | Create Account
2 | View Restaurants
3 | Search Restaurants
4 | View Menu
5 | Add to Cart
6 | Purchase
7 | Restaurant views order
8 | Restaurant marks order as delivered
# | Notes:
1 | The above points were listed as draft ideas by the project sponsor.
2 | The project sponsor mentioned that he wants to compete against Talabat.
3 | As a sponsor, I am planning to compete against Talabat.
4 | This is a view only file, you can make a copy then edit in the copy.
5 | You can find a tab named Product Backlog Template, please feel free to use it when creating your product backlog.